## Slide 1: Secure Modem Development Plan
Workshop Day 1 Session 2

## Slide 2: Content
System Overview
Development Plan
Discussion

## Slide 3: System Overview
Modem Description
Processing Blocks
Software vs Hardware
Implementation Plan

## Slide 4: Modem Description
  It is applicable for
    Military personnel on field
    Government official in office
  It is portable and has compact dimension
  It generates signal on voice frequency
  It has basic features (transmit / receive data and voice)

## Slide 5: Modem Description Cont.

## Slide 6: Processing Blocks
Voice Encoder or data buffer
Encryptor
Modulator

## Slide 7: Encoder Implementation
On Hardware 
[+] Low output latency since the IC is specifically designed for encoding
On Software
[-] Slower encoding process
[+] Faster implementation by using available library

## Slide 8: Encryptor Implementation
On Hardware
[+] Faster encryption process
[-] Needs longer time to develop custom algorithm
On Software 
[-] Slower encryption process
[+] Faster option to implement custom algorithm

## Slide 9: Modulator Implementation
On Hardware
[+] Low output latency since the IC is specifically designed for modulation
[-] Needs longer time to develop modulation algorithm
On Software 
[-] Slower modulation process
[+] Faster implementation by using available library

## Slide 10: Implementation Plan

## Slide 11: Development Plan
Description
Timeline
Deliverables

## Slide 12: Description
Development for PoC
Hardware Encoder/Decoder
  Use dedicated vocoder
Software Encryptor
  Use public algorithm
Software Modulator
  Use multiple-carriers modulation

## Slide 13: Timeline
Develop hardware platform
4 months
Implement software encryptor and modulator
3 months *
Integrated System
2 months
*may use available implementation from Lemsaneg

## Slide 14: Deliverables
Work Package | Activities | Deliverables | Encoder | Encryptor and Modulator*
System design | Explore implementation method | System design doc | 1 month | 1 month
 | Design module |  |  | 
System delivery | Develop module | Readiness for integration | 3 months | 2 months
 | Internal testing |  |  | 
System integration | Integrated System | Readiness for testing | 2 months | 
System testing | On-site test with Lemsaneg | Test report | 1 week | 
*may use available implementation from Lemsaneg

## Slide 15: Discussion